## Sheet1
RBM Malaria in Pregnancy Working Group Workplan, 2023-2024
| Activities | Responsible Partner/ Contributing Partner | Timeline | Notes
1 | Policy
1.1 | Support dissemination of WHO Field Guide for C-IPTp | WHO | Completed
2 | Advocacy
2.1 | Continue to support SpeedUp ScaleUp IPTp campaign | MMV | Ongoing
2.2 | Webinar/teleconference for a few countries to present on successful community engagement | Jhpiego | Completed
3 | Programmatic initiatives, products and tools
3.1 | Disseminate existing SBC CHW toolkit for integration into ANC promotion & MiP interventions | SBC WG | Q1, Q2, Q3
3.2 | Support establishment/revitalization/maintenance of country level MiP WGs. This will include use of MiP TWGs tookit and sample TORs | Jhpiego/PSI through IMPACT Malaria | Completed
3.3 | Build capacity of NMCPs in gender through gender in malaria training webinar
3.4 | ANC Uptake Manuscript Development | Uniformed Services University | Q1, Q2
3.5 | Establish WhatsApp business function to re-introduce/disseminate key WG tools to wider MiP community, including new MOH staff | Coordinator
3.6 | Pending outcome of GDG, develop brief to reinforce existing recommendations on the treatment of vivax malaria in pregnant women. | ? | ?
3.7 | Facilitate establishment of new manufacturers of QA SP | MMV | Ongoing
3.8 | Review OTSS for quality integrated supportive supervision | Jhpiego/PSI through IMPACT Malaria | Completed
3.9 | Support country-level implementation and scale-up of C-IPTp | Jhpiego/SBC WG | Ongoing
4 | M&E
4.1 | Update and re-disseminate MiP M&E brief | MiP/SME WG | Q1, Q2
4.2 | Review malaria matchbox survey | CDC/USAID | Q2, Q3
4.3 | Engage ALMA to incorporate IPTp as scorecard indicator | CDC/ALMA/GF | Q2, Q3
4.3 | Collect and disseminate data on prevalence of SP resistance markers | PMI/CDC/WHO | Ongoing | TES/TIPTOP/SMC work
5 | Research
5.1 | Identify new drugs which are safe in 1st trimester | MMV | Ongoing
5.2 | Qualitative studies on gender about how best to talk with pregnant women | CEGENSA?
5.3 | Formative research around how to get adolescents to attend ANC | CEGENSA?
5.4 | Qualitative research on barriers to early ANC | PMI
5.5 | Share research activities and key findings with the WG through teleconferences and other opportunities throughout the year as appropriate, including: a. IPTp-DP with or without azithromycin in HIV uninfected women b. IPTp-DP in HIV infected women taking CTX | LSTM/Research partners | Completed
5.6 | Support R&D drug research in pregnant and lactating women including (1) Investigation of new pre-clinical models that could be used to prioritize appropriate compounds (2) Identification of a new SP drug alternative for preventing malaria in pregnancy based on WHO’s Preferred Product Characteristics (PPCs), (3) Generation of new evidence on ACTs use in all trimesters (4) Research on the potential of IPTp-DP in HIV+ pregnant women population and cardio safety of IPTp-DP as a single dose (5) PKPD dose adjustment modelling MMV and research partners | MMV/LSHTM/LSTM | Ongoing
5.7 | Share research activities and key findings with the WG through teleconferences and other opportunities throughout the year as appropriate specific to trial results from Zambia, including: a. Measurement the protective effect of SP alone vs SP plus metronidazole vs DP plus metronidazole deliered as IPTp to improve pregnancy outcomes among HIV uninfected women b. Acceptability studies of the interventions c. Cost effectiveness of the interventions | London School of Hygiene & Tropical Medicine | Ongoing
5.8 | Measure the cardiac effect of DP versus SP among asymptoamtic pregnant women with and without malaria infecction, as well as the day 28 parasite clearance rate of SP | London School of Hygiene & Tropical Medicine and Medicines for Malaria Venture | Ongoing
5.9 | Assess the efficacy of alternative pharmaceuticals (ie: vaccines and monoclonal antibodies) for MiP | NIH/Sanaria | Ongoing
5.1 | Support research on implementation of ANC 8 contact model leads to higher uptake of IPTp by Expertise France and WHO in Mali | WHO | Ongoing | 3 year project starting in Jan. 2021
6 | Coordination
6.1 | Convene MIP WG teleconferences and include country TWG representatives | Secretariat | Every 2 months
6.2 | Continued collaboration with RBM Secretariat and other WGs to ensure effective support; including consistent participation in CRSPC meetings | Co-chairs; All partners | Ongoing
6.3 | Continue to engage Country Advisory Board and support coordination through regional networks | Co-chairs | Ongoing
6.4 | Engender coordination between RMNCH & MiP through support of GFF resource mobilization; inform malaria community of this opportunity through webinar/teleconference on how to engage in this process | World Bank/RBM | Completed
6.5 | Look for opportunities to coordinate with groups supporting adolescent girls and other underserved groups, including webinar around adolescence and MiP | co-Chairs | Ongoing
6.6 | Advocate for and identify ways to increase ownership and use of ITNs by women of reproductive age | co-Chairs | Q2, Q3